## Slide 1: Monthly Study Progress Meeting
Oranicha Buthphorm
11 Jan, 20
Naresuan University
Phisanulok

## Slide 2: Outline
Study plan & Update actual done
Activities done
Next activities
Problem and solution
Other
1 mns

## Slide 3
No. | Topics | Dec’19 | Jan’ 20 | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
1 | Further proposal, further draft of 1st publish | x |  |  |  |  |  |  |  |  |  |  |  | 
2 | Final Proposal, further work 1st publish |  | x |  |  |  |  |  |  |  |  |  |  | 
 | Proposal Defense, Final 1st publish, submit 1st |  |  | x |  |  |  |  |  |  |  |  |  | 
3 | Research Tools Quality check |  |  |  | x |  |  |  |  |  |  |  |  | 
4 | Data collection |  |  |  |  | x | x | x |  |  |  |  |  | 
 | Data collection, Data Verify |  |  |  |  | x | x | x |  |  |  |  |  | 
5 | Data Analysis, draft for int’l conference |  |  |  |  | x | x | x |  |  |  |  |  | 
 | Discuss conclusion, draft ch 4-5, final paper for conf. |  |  |  |  |  |  |  | x |  |  |  |  | 
6 | Draft for 2nd paper, Submit for conf. |  |  |  |  |  |  |  |  | x |  |  |  | 
 | Final for ch 1-5, final for 2nd paper |  |  |  |  |  |  |  |  |  | x |  |  | 
7 | Submit 2nd paper, prepare for defense |  |  |  |  |  |  |  |  |  |  | x |  | 
8 | Dissertation Defense, Modification |  |  |  |  |  |  |  |  |  |  |  | x | 
9 | Format checking, Final Dissertation |  |  |  |  |  |  |  |  |  |  |  |  | x
Study plan

## Slide 4: Update actual done
Thesis Proposal
2nd draft of 1st publish

## Slide 5: Activities done from monthly meeting on 13 Nov.19
Identify primary stakeholder, secondary-in thesis proposal
Southern line demand- 1st publish and thesis proposal
Review research plan- thesis proposal
Review whole thesis proposal……more satisfy..wait for green line
Further draft on 1st publish…not complete, not good yet
On field surveyed- Nakhon Pathom, Chumporn, Trang, Sonkla, Padang Besar

## Slide 6: Thesis proposal Foster Factors to Rail Freight in Southern of Thailand
Background and Significance of the Study
Purposes of the Study
Statement of the Problems
Scope of the Study
Related Works and Studies
Research Procedures of the Study

## Slide 7: Research Procedures of the Study
  Field data and participants
  Variables in the Research
  Research Instruments and Instrument Development
Data Collection
Primary Sources , secondary data sources
Data Analysis and Management

## Slide 8: Research Instruments
A sample of in-depth interview questions and focus group discussion (A)
  21 questions
A sample of in-depth interview questions guide (B)
  The interview consists of 5 parts
Observation Form (C)

## Slide 9: Next activities
Jan. 20
  Final 1st publish in Jan, 20
  Prep for proposal defense
Feb.20
  Proposal Defense, Final 1st publish,
  submit 1st publish
  The Asian Journal of Shipping and Logistics- QTR 3, Free APC
  https://www.journals.elsevier.com/the-asian-journal-of-shipping-and-logistics
  International Journal of Rail Transportation- abt 1800 USD
  Journal of Rail Transport Planning & Management abt 1800 USD

## Slide 10: Next activities (cont.)
Mar.20
Research Tools Quality check

## Slide 11: Problem and solution
Time management--try to find out better time management tool/techniques once you study, work in the same time……..with various method and guru
Health-- try to balance life and for keep body healthy not sick, eyeach, headche, migrane, sleep too much or not sleep
Motivation----Model-----

## Slide 12: Other
Coordinate with committee and academic staff for proposal defense appointment date within Feb, 20